## Approach
Data Set ID: |  |  | CMDB reference / Changelog
Data Set Name: | CoE - Analysis |  | Integration ID: | Integration Name:
|  |  | Transformation ID: | Transformation Name:
Responsible Customer: | Aker BP |  | Change description:
Responsible Tech Leader: | Stéphanie Raoul
Approach
Scope and objectives: The scope of this test plan is to succesfully complete User Acceptance Tests in accordance with the following objectives:
1. Extract and transform time series data from CDF Clean using Cognite Functions. | 2. Check that new time series is of correct data object and populated with correct data | 3. Write dataset to CDF done successfully
Outside the scope: Test that Lowess smoothing of signal is reasonable
Premisses: Request for needed read/write access from/to CDF Dev and CDF Prod has been accepted
Strategy: 1. Retrieve time series data from CDF Prod using Cognite Functions 2. Transform signal using Cognite Functions, statsmodels and numpy 3. Check that new time series has been populated with filtered signal, and assigned to correct dataset
Risks: Low risk
Test Environment: Aker BP - Test environment (akerbp-test)

## SIT Plan
Data Integration Name:
Test Type : | SIT
Test date:
Test performed by:
Test id | Test group | Test Case Description | Actions |  | Actual result | Description |  |  |  |  | Obs
|  |  | Steps to execute the test | Expected Result |  | Pass | Fail | Accep. fail | N/A | Comment
SIT-1: Full load | Load records where integration is triggered manually | Test full load of records from <source> to CDF Raw | 1. Delete all events of types Electric Motor and Intrumentation from the last day in CDF 1. Delete all existing entries in Akerbp-test tenant CDF.Raw database <AizeEventsToSAP.AizeEventsToSAP> 3. Create 10 events in Aize 3. Run Cognite function 4. Check in the Raw table that all the logs are 201 | Number of <items> transferred to CDF Raw is the same as number of entries in <source>. LastSuccessfulRun timestamp in the integration configuration database is updated to the newest timestamp from the <source>.
SIT-2: Delta load | Delta load of records where integration runs on the scheduled timing | Delta load of new - updated - voided records from <source> where integration runs on the scheduled timing | 1. Enable the scheduled trigger for <source>, confirm it is working. 2. Wait for trigger execution being completed. While the integration is running, check integration monitoring tools for progress and errors. 3. Verify the number of entries transferred to CDF Raw both in <source> and CDF Raw 4. Verify that LastSuccessfulRun timestamp in the integration configuration database is correct. | No <items> are updated in CDF Raw. LastSuccessfulRun timestamp in the integration configuration database is correct.
SIT-3: Integration down | <source> is not reachable | Testing of the scenario when the source system is not available. | 1. Manually update the URL to <source> database imitating the <source> database is unreachble. 2. Wait for trigger execution being completed. While the integration is running, check integration monitoring tools for progress and errors. 3. Expect to see the failure error message in the integration monitoring tool and BizTalk server Event Log. 4. Verify that LastSuccessfulRun timestamp in the integration configuration database is NOT updated. 5. Verify the number of entries transferred to CDF Raw is 0 in CDF. | Integration server handles the error, logs it accordingly. LastSuccessfulRun timestamp in the integration configuration database is NOT updated.
| CDF API is not reachable | Testing of the scenario when the destination system is not available. | 1. Manually update the URL to CDF API imitating that it is unreachble. 2. Wait for trigger execution being completed. While the integration is running, check integration monitoring tools for progress and errors. 3. Expect to see the failure error message in the integration monitoring tool and BizTalk server Event Log. 4. Verify that LastSuccessfulRun timestamp in the integration configuration database is NOT updated. 5. Verify the number of entries transferred to CDF Raw is 0 in CDF. | Integration server handles the error, logs it accordingly. LastSuccessfulRun timestamp in the integration configuration database is NOT updated.
| Restore after down-time | Test integration when normal operations is restored | 1. Check delta load runs as expected 2. Check backfill of records after down-time | Integration runs as normal Records are loaded correctly.
Note on G6: Morten Melstrøm: Error description A - Critical - The whole or a substantial part of operational service is unavailable. B - Serious - Some critical functions do not work, or works with significantly poorer response times than agreed. C - Less serious - Non-critical functions do not work, reduced response time compared to what has been agreed. D - Negligible - The fault has little effect on the solution. Typically the cosmetic nature.

## UAT Plan
Data Integration Name:
Test type: | UaT
Test date:
Test performed by:
Comments: | Variable client is and instance of CogniteClient()
Test id | Test group | Test Case Description | Actions |  | Actual result | Description |  |  |  |  | Obs
|  |  | Steps to execute the test | Expected Result |  | Pass | Fail | Accep. fail | N/A | Comment
UaT-1 | Retrieve time series from akerbp-prod | Retrieve time series using Cognite Functions | 1. Call client.time_series.retrieve with external id of dataset as argument | a. Function call returns successfully
|  |  | 2. Check output of function call | b. Correct time series has been retrieved, including metadata
UaT-2.1 | Create time series object | Create new time series data object using Cognite Functions | 1. Create an instance of TimeSeries resource type | a. New TimeSeries instance created
|  | Test that object is of correct type and assigned to correct dataset | 2. Call client.time_series.create with the new TimeSeries object as argument | b. New time series object created and assigned to correct dataset
|  |  | 3. Check output of function call | c. No duplicated time series
UaT-2.2 | Insert datapoints into new time series | Insert datapoints into new time series object using Cognite Functions | 1. Call client.time_series.data.insert_dataframe on new time series with some input data | a. Function call runs successfully
|  | Test that time series is populated with correct data | 2. Check status of function call | b. New time series populated with correct data
3. Verify that time series has been populated with correct data
UaT-2.3 | Delete time series |  | 1. Delete time series using client.time_series.delete | a. Function call runs successfully
|  | Delete time series object using Cognite Functions | 2. Return list of all time series in akerbp-prod and check that out time series is non-existing | b. Our time series is deleted from list of time series
|  |  | 3. Records are deleted in accordance to defined business rules | c. Handling of deleted records is according to defined business rules
UaT-3.1 | Verify lowess smoothing | Test if signal has been filtered | 1. Smooth signal using nonparametric.lowess function from statsmodels.api module | a. Function nonparametric.lowess runs successfully
|  |  | 2. Check if signal has actually been smoothed | b. Smoothed signal lies between min and max values of local datapoints used for filtering
UaT-3.2 | Test function locally before deploying to CDF Dev | Test locally before instantiating and calling as Cognite Function | Run handle function as a "dry run" (i.e., not deploying time series data to CDF | Local modifications to handle function: a) Create dummy time series not linked to any dataset
b. Insert calculated datapoints into dummy time series.
c. Check that time series is populated with correct data
d. Delete dummy time series from CDFs repository
Note on G7: Morten Melstrøm: Error description A - Critical - The whole or a substantial part of operational service is unavailable. B - Serious - Some critical functions do not work, or works with significantly poorer response times than agreed. C - Less serious - Non-critical functions do not work, reduced response time compared to what has been agreed. D - Negligible - The fault has little effect on the solution. Typically the cosmetic nature.

## UaT - test scenarios
Test scenarios
UaT test ID | Test case | Item to be tested | Test result | Contextualized to node in CDF Asset hierarchy
<UaT-1/UaT2> | 1 | <external id or name> | <actual item in CDF or comment on findings> | <node in CDF Asset hierarchy>
<UaT-1/UaT2> | 2 | <external id or name> | <color code pass-no pass> | <node in CDF Asset hierarchy>
<UaT-1/UaT2> | 3 | <external id or name> |  | <node in CDF Asset hierarchy>
<UaT-1/UaT2> | N | <external id or name> |  | <node in CDF Asset hierarchy>

## UaT - contexualization rules
Contextualization rules
Entity | Rule | Contextualization field | Procedure | Comment | Example
<data set> | Match to CDF Asset hierarchy | <raw table>.<field>
If no match in CDF Asset hierarchy

## UaT - data model
Data model
The data model should show Raw tables used in the transformation to the <data set>.